## Slide 1
GUJARAT QUANTUM MISSION
Build access first.
Prove demand.
Scale what works.
Executive roadmap for Government of Gujarat and institutional discussions
Decision package • Evidence checked 1 October 2026
Planning draft — no outreach sent
Notes: Sources checked 1 October 2026:
https://dst.gov.in/node/7223
https://dst.gujarat.gov.in/dst/Home/stip

## Slide 2
DECISION REQUESTED
The decision is to create a mission operating system—not a building
GUJARAT QUANTUM MISSION • EXECUTIVE ROADMAP • 02
1 OCT 2026
Authorize now
• Mission sponsor and 90-day mandate
• Small secretariat and technical council
• Institution/facility audit
• Structured access talks with all four NQM hubs
Do not pre-commit
• Large standalone capital facility
• Technology-first pilots without owners
• Claims of quantum advantage without baselines
• Counting tenders, demos or affiliations as operational capacity
Decision at day 90
Approve 3–5 stage-gated pilots, first-year budget, access agreements and talent programme only after evidence is complete.
Notes: Sources checked 1 October 2026:
https://dst.gov.in/node/7223
https://dst.gujarat.gov.in/dst/Home/stip

## Slide 3
NATIONAL ARCHITECTURE
National Quantum Mission already provides the backbone Gujarat should use
GUJARAT QUANTUM MISSION • EXECUTIVE ROADMAP • 03
1 OCT 2026
₹6,003.65 crore
Cabinet-approved mission envelope
2023-24 to 2030-31
COMPUTING
FQCI • IISc
Access, algorithms, translation
COMMUNICATION
Samgnya • IIT Madras
QKD, networks, components
SENSING & METROLOGY
Qmet • IIT Bombay
Sensors, standards, field validation
MATERIALS & DEVICES
QMD • IIT Delhi
Devices, fabrication, components
Gujarat’s advantage comes from structured access and co-owned work packages—not duplicating every national facility.
Notes: Sources checked 1 October 2026:
https://www.pib.gov.in/newsite/erelcontent.aspx?lang=2&reg=48&relid=243079
https://dst.gov.in/node/7223
https://dst.gov.in/node/7834

## Slide 4
CURRENT-STATE AUDIT
Gujarat has credible nodes, but capability and access remain fragmented
GUJARAT QUANTUM MISSION • EXECUTIVE ROADMAP • 04
1 OCT 2026
NODE
KNOWN ROLE
NEXT VERIFICATION
STATUS
PRL
Quantum science and optics
Inventory equipment and external access
Operational research
SAC / ISRO Ahmedabad
Quantum communication
Clarify node role, readiness and permissible access
Demonstrated
IIT Gandhinagar
Research, talent, Qmet participation
Map work packages and facilities
Operational
GSV
Transport/logistics application
Verify project, users and datasets
Sanctioned
ISR
Field sensing testbed
Define measurement problem and baseline
Operational
GIL / GIFT / IFSCA
Procurement and regulated demand
Verify tender-to-operation chain; define PQC pilot
Mixed
Notes: Sources checked 1 October 2026:
https://dst.gov.in/node/7834
https://www.prl.res.in/
https://www.isro.gov.in/
https://iitgn.ac.in/
https://gsv.ac.in/
https://isr.gujarat.gov.in/
https://gil.gujarat.gov.in/tenders
https://ifsca.gov.in/

## Slide 5
HUB ACCESS PLAN
Open four national access channels in parallel
GUJARAT QUANTUM MISSION • EXECUTIVE ROADMAP • 05
1 OCT 2026
1
FQCI
Computing access, algorithms, startup and challenge programmes
2
Samgnya
QKD/network work, ISRO Ahmedabad node and component teams
3
Qmet
IITGN-linked sensing projects, metrology and NextSense route
4
QMD
Device design, materials, fabrication and packaging pathway
Every meeting must close with: named counterpart • eligible programme • access conditions • cost • IP/data terms • first joint action.
Notes: Sources checked 1 October 2026:
https://qcinnovation.co.in/programs/
https://www.samgnya.in/startups
https://qmettech.com/portfolio/nextsense-call-for-proposal/
https://qmd.iitd.ac.in/

## Slide 6
INDIA LESSONS
State benchmarks point to disciplined translation, not imitation
GUJARAT QUANTUM MISSION • EXECUTIVE ROADMAP • 06
1 OCT 2026
Infrastructure-led
Andhra Pradesh: visible computing-centre model.
Lesson: verify procurement, access, utilization and operating economics before replication.
Cluster-led
Karnataka and Telangana: park/cluster and anchor-partner models.
Lesson: build networks around committed institutions and industry demand.
Policy-led
Tamil Nadu and other states: deep-tech incentives and mission activity.
Lesson: stage support by technical and customer milestones.
Gujarat should combine three elements
ACCESS
Use national hubs and existing infrastructure
DEMAND
Select problems with asset owners and baselines
TRANSLATION
Fund milestones, validation and procurement pathways
Notes: Sources checked 1 October 2026:
https://www.ap.gov.in/
https://ksteps.karnataka.gov.in/
https://it.telangana.gov.in/
https://startuptn.in/

## Slide 7
GLOBAL OPERATING MODEL
International leaders use a portfolio with explicit gates
GUJARAT QUANTUM MISSION • EXECUTIVE ROADMAP • 07
1 OCT 2026
MISSION
Long-horizon public commitment
HUBS
Concentrated scientific leadership
TESTBEDS
Shared infrastructure and real environments
CHALLENGES
User-led calls with measurable outcomes
TALENT
Research, engineering and technician pathways
ASSURANCE
Standards, benchmarking and responsible claims
Replicate the operating logic; do not copy another country’s spending level or institutional shape.
Notes: Sources checked 1 October 2026:
https://www.gov.uk/government/publications/national-quantum-strategy
https://www.quantum.gov/
https://qt.eu/
https://ised-isde.canada.ca/site/national-quantum-strategy/en
https://www.industry.gov.au/publications/national-quantum-strategy

## Slide 8
PRIORITY PORTFOLIO
Start with a balanced portfolio of near-, mid- and long-horizon work
GUJARAT QUANTUM MISSION • EXECUTIVE ROADMAP • 08
1 OCT 2026
0–18 MONTHS
PQC / crypto-agility
Quantum network assurance
Hub access and teaching labs
12–36 MONTHS
Field sensing validation
Logistics and grid benchmarks
Component qualification
24–60 MONTHS
Devices and packaging
Space-quantum subsystems
Selective molecular simulation
Pilot gate: named user + baseline + data/access + national partner + measurable stop/go test.
Notes: Sources checked 1 October 2026:
https://dst.gov.in/node/7223
https://ifsca.gov.in/
https://qmettech.com/
https://qmd.iitd.ac.in/

## Slide 9
GOVERNANCE
A small mission office should orchestrate a distributed system
GUJARAT QUANTUM MISSION • EXECUTIVE ROADMAP • 09
1 OCT 2026
MISSION GOVERNING BOARD
MISSION SECRETARIAT / PMO
Scientific council
Technical quality and claims
Hub access office
National programmes and facilities
Demand & pilots
Problem owners and stage gates
Talent & ecosystem
Universities, startups and skills
Assurance & data
Standards, security, IP and evidence
Funding follows evidence: audit → concept → validation → deployment → scale.
Notes: Sources checked 1 October 2026:
https://dst.gov.in/node/7493
https://dst.gujarat.gov.in/dst/Home/stip

## Slide 10
LAUNCH SEQUENCE
The first 90 days convert uncertainty into an investable plan
GUJARAT QUANTUM MISSION • EXECUTIVE ROADMAP • 10
1 OCT 2026
DAYS 0–15
Mandate and sponsor
Secretariat
Send questionnaires
DAYS 15–45
Facility visits
Four hub meetings
25 problem statements
DAYS 45–75
Score 3–5 pilots
Draft access terms
Claims/data protocol
DAYS 75–90
Costed year-one plan
Talent consortium
Baseline report
Day-90 output: verified capability map + demand portfolio + hub access terms + first-year decision memo.
Notes: Sources checked 1 October 2026:
https://dst.gov.in/node/7834
https://qcinnovation.co.in/programs/
https://www.samgnya.in/startups
https://qmettech.com/
https://qmd.iitd.ac.in/

## Slide 11
FIVE-YEAR ROADMAP
Scale only after independent evidence of use and value
GUJARAT QUANTUM MISSION • EXECUTIVE ROADMAP • 11
1 OCT 2026
PHASE 1
0–6 months
Audit, access, governance, 3–5 pilots
PHASE 2
6–18 months
Validated pilots, teaching labs, startup pipeline
PHASE 3
18–36 months
Selective shared facilities and procurement pathways
PHASE 4
36–60 months
Multi-site deployment and proven specialization
Scale gate: sustained users • utilization • independently validated performance • operating budget • procurement/market route.
Notes: Sources checked 1 October 2026:
https://www.gov.uk/government/publications/national-quantum-strategy
https://ised-isde.canada.ca/site/national-quantum-strategy/en

## Slide 12
IMMEDIATE DECISIONS
Approve five actions to begin
GUJARAT QUANTUM MISSION • EXECUTIVE ROADMAP • 12
1 OCT 2026
1
Name the mission sponsor and nodal department
2
Authorize the 90-day audit and engagement programme
3
Invite all four NQM hubs to structured access meetings
4
Require 25 owner-backed problem statements before pilot selection
5
Return on day 90 with a costed, evidence-linked first-year plan
Operating principle: access first • evidence before claims • demand before capex • gates before scale
Notes: Sources checked 1 October 2026:
https://dst.gov.in/node/7223
https://dst.gujarat.gov.in/dst/Home/stip